## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | Project setup, Java basics training, and environment configuration | MUST HAVE | NA | Tarun Harinkhede | 3- Completed
Sprint 1 | Sprint 1 | US-02 | Implement Account module with account creation and balance handling | MUST HAVE | NA | Tarun Harinkhede | 3- Completed
Sprint 2 | Sprint 2 | US-03 | Implement deposit, withdrawal, and transfer operations | MUST HAVE | US-02 | Tarun Harinkhede | 3- Completed
Sprint 2 | Sprint 2 | US-04 | Add transaction validation and exception handling | MUST HAVE | US-03 | Tarun Harinkhede | 3- Completed
Sprint 3 | Sprint 3 | US-05 | Implement low balance alert and email notification module | SHOULD HAVE | US-02 | Tarun Harinkhede | 3- Completed
Sprint 4 | Sprint 4 | US-06 | Develop simple frontend for account and transaction operations | COULD HAVE | NA | Tarun Harinkhede | 3- Completed
Sprint 4 | Sprint 4 | US-07 | Integrate frontend with backend and perform end-to-end testing | SHOULD HAVE | US-06 | Tarun Harinkhede | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 28 | 19 | 17 | 12 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US -01 | T1 | Java basics training, and environment configuration | 2025-12-01 | 2025-12-03 | Tarun Harinkhede,Iswar Patra, Dharanish Vijayakumar,Vijay kolla, Sourabha halli | Project setup | complete | 4 | Day 1: 3; Day 2: 2; Day 3: 2
US -02 | T2 | Created account module with account creation and balance handling | 2025-12-04 | 2025-12-07 | Tarun Harinkhede,Iswar Patra, Dharanish Vijayakumar,Vijay kolla, Sourabha halli | Module creation | complete | 4 | Day 1: 2; Day 2: 3; Day 3: 2; Day 4: 1
US -03 | T3 | Method creation such as deposit, withdrawal, and transfer operations | 2025-12-08 | 2025-12-10 | Tarun Harinkhede,Iswar Patra, Dharanish Vijayakumar,Vijay kolla, Sourabha halli | Method creation | complete | 4 | Day 1: 3; Day 2: 2; Day 3: 2
US -04 | T4 | Performed transaction validation and exception handling | 2025-12-11 | 2025-12-16 | Tarun Harinkhede,Iswar Patra, Dharanish Vijayakumar,Vijay kolla, Sourabha halli | Exception handling | complete | 4 | Day 1: 3; Day 2: 2; Day 3: 1; Day 4: 1; Day 5: 1
US -05 | T5 | Created low balance alert and email notification module | 2025-12-17 | 2025-12-21 | Tarun Harinkhede,Iswar Patra, Dharanish Vijayakumar,Vijay kolla, Sourabha halli | Alert and Email | complete | 4 | Day 1: 2; Day 2: 3; Day 3: 2; Day 4: 1; Day 5: 1
US -06 | T6 | Frontend for account and transaction operations | 2025-12-22 | 2025-12-25 | Tarun Harinkhede,Iswar Patra, Dharanish Vijayakumar,Vijay kolla, Sourabha halli | Frontend | complete | 4 | Day 1: 3; Day 2: 3; Day 3: 2; Day 4: 1
US -07 | T7 | Integrate frontend with backend | 2025-12-26 | 2025-12-28 | Tarun Harinkhede,Iswar Patra, Dharanish Vijayakumar,Vijay kolla, Sourabha halli | Integration and testing | complete | 4 | Day 1: 3; Day 2: 2; Day 3: 1
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Project Setup | NA
Sprint 1 | Day 4 | Account module | solved syntax error
Sprint 2 | Day 8 | Transaction module | NA
Sprint 2 | Day 11 | Create,deposite,withdraw methods | NA
Sprint 3 | Day 17 | Alert module, Email notification | checked different email for alert
Sprint 4 | Day 22 | Implement Frontend | solved basic structural error
Sprint 4 | Day 25 | Integration Testing | NA
Sprint 4 | Day 28 | Fronted + Backend Integration Testing | NA

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-12-01 | 2025-12-07 | Tarun Harinkhede | Project Setup,Java basics | complex planning | Create account module | solved environment configuration
2 | Sprint 2 | 2025-12-08 | 2025-12-14 | Iswar Kumar Patra | Create transaction module | creating extra methods | create methods like deposit,withdraw,transfer | NA
3 | Sprint 3 | 2025-12-15 | 2025-12-21 | Dharanish Vijayakumar | Create alert module | writing long mail message | checking email notification module | tried different email to test alert
4 | Sprint 4 | 2025-12-22 | 2025-12-28 | Vijay Karthik Kolla | Implement simple frontend | advance css style | integration testing | NA
5 |  |  |  | Sourabha Shrenikraja Halli
6
7